## SQL CAF Project Task List
Work Item Type | Title | Priority | Assigned To | State | Iteration Path
Epic | CAF SQL Migration Project Plan | 1 |  | New | SQL_CAF SQL Migration
Feature | Strategy, Plan, Readiness | 2 |  | New | SQL_CAF SQL Migration
User Story | Define Strategy | 2 |  | New | SQL_CAF SQL Migration
Task | Define Strategy CAF Plan Template | 2 |  | New | SQL_CAF SQL Migration
Task | Define Business Motivations, Security, Cost and Innovation strategies | 2 |  | New | SQL_CAF SQL Migration
User Story | Plan and Assessment | 2 |  | New | SQL_CAF SQL Migration
Task | Digital Estate: Collect Current Inventory | 2 |  | New | SQL_CAF SQL Migration
Task | Align assets to cloud offerings to calculate pricing | 2 |  | New | SQL_CAF SQL Migration
Task | Initial Organization Alignment | 2 |  | New | SQL_CAF SQL Migration
Task | Skills Readiness Plan | 2 |  | New | SQL_CAF SQL Migration
Task | Develop Cloud Adoption plan | 2 |  | New | SQL_CAF SQL Migration
User Story | CAF SQL Migration Readiness | 2 |  | New | SQL_CAF SQL Migration
Task | Azure Setup Guide | 2 |  | New | SQL_CAF SQL Migration
Task | Pros and Cons of Landing Zones and Migration Tools Decision Guide | 2 |  | New | SQL_CAF SQL Migration
Task | Decide and Create Landing Zone | 2 |  | New | SQL_CAF SQL Migration
Task | Migrate SSIS, SSAS and SSRS to Azure | 2 |  | New | SQL_CAF SQL Migration
Task | Examples of Selecting Landing Zone | 2 |  | New | SQL_CAF SQL Migration
Feature | CAF SQL Migration | 2 |  | New | SQL_CAF SQL Migration
User Story | Migration of On-Prem to Azure VM | 2 |  | New | SQL_CAF SQL Migration
Task | OnPrem to Azure Virtual Machine Overview | 2 |  | New | SQL_CAF SQL Migration
Task | Assessment | 2 |  | New | SQL_CAF SQL Migration
Task | Deployment and Migration Testing | 2 |  | New | SQL_CAF SQL Migration
Task | Release and Additional Resources | 2 |  | New | SQL_CAF SQL Migration
User Story | Migration - On-Prem to Azure SQL Database | 1 |  | New | SQL_CAF SQL Migration
Task | OnPrem to Azure Virtual Machine Overview | 2 |  | New | SQL_CAF SQL Migration
Task | Assessment | 2 |  | New | SQL_CAF SQL Migration
Task | Deployment and Migration Testing | 2 |  | New | SQL_CAF SQL Migration
Task | Release and Additional Resources | 2 |  | New | SQL_CAF SQL Migration
User Story | Migration - On-Prem to Azure SQL Managed Instance | 2 |  | New | SQL_CAF SQL Migration
Task | OnPrem to Azure Virtual Machine Overview | 2 |  | New | SQL_CAF SQL Migration
Task | Assessment | 2 |  | New | SQL_CAF SQL Migration
Task | Deployment and Migration Testing | 2 |  | New | SQL_CAF SQL Migration
Task | Release and Additional Resources | 2 |  | New | SQL_CAF SQL Migration
Feature | CAF SQL Migration - Governance and Manage | 2 |  | New | SQL_CAF SQL Migration
User Story | SQL Migration - Governance | 2 |  | New | SQL_CAF SQL Migration
Task | Organize reqources | 2 |  | New | SQL_CAF SQL Migration
Task | Manage Access | 2 |  | New | SQL_CAF SQL Migration
Task | Manage Costs | 2 |  | New | SQL_CAF SQL Migration
Task | Governance, Security and Compliance | 2 |  | New | SQL_CAF SQL Migration
Task | Monitoring and Reporting | 2 |  | New | SQL_CAF SQL Migration
Task | Manage Governance (Inventory / Operational Compliance) | 2 |  | New | SQL_CAF SQL Migration
Feature | STAKEHOLDER SIGN OFF AND CLOSURE | 2 |  | New | SQL_CAF SQL Migration
User Story | CAF SQL Migration Project Review and Closer | 2 |  | New | SQL_CAF SQL Migration
Task | SQL Data Migration Project review meeting | 2 |  | New | SQL_CAF SQL Migration
Task | SQL Data Migration documents review | 2 |  | New | SQL_CAF SQL Migration
Task | Sign off on Project delivery | 2 |  | New | SQL_CAF SQL Migration