## SQL CAF Project Task List
Work Item Type | Title | Description | Priority | Assigned To | State | Iteration Path
Epic | CAF SQL Migration Project Plan | Build a Project Plan to track SQL Migration using Cloud Adoption Framework | 1 |  | New | SQL_CAF SQL Migration
Feature | Strategy, Plan, Readiness | Guidance on Strategy, Plan and Readiness phases | 2 |  | New | SQL_CAF SQL Migration
User Story | Define Strategy | Define business justification and expected outcomes of adoption | 2 |  | New | SQL_CAF SQL Migration
Task | Define Strategy CAF Plan Template | * Document decisions while executing the cloud adoption strategy and plan * Use the template to organize the decisions and data points that will align the template for the cloud adoption plan with specific plans for adoption * List business priorities, timelines and milestones in the upcoming year for successful cloud adoption | 2 |  | New | SQL_CAF SQL Migration
Task | Define Business Motivations, Security, Cost and Innovation strategies | * Identify business motivations based on critical business events, migration motivations and innovation motivations * List the operational and capital expenses required for cloud adoption * Identify security protocols and compliance issues regarding data or applications * Collect motivations focussed more on an innovate strategy | 2 |  | New | SQL_CAF SQL Migration
User Story | Plan and Assessment | Align actionable adoption plans to business outcomes | 2 |  | New | SQL_CAF SQL Migration
Task | Digital Estate: Collect Current Inventory | * List IT assets that supports specific business applications for later analysis and rationalization * Use Data Migration Assistant to assess feature parity between SQL sources and targets * Use Azure Migrate to assess the migration suitability of the machines * Use Service Map in Azure Migrate to show dependencies between machines to be migrated | 2 |  | New | SQL_CAF SQL Migration
Task | Align assets to cloud offerings to calculate pricing | * Build a costing model for each asset in the digital estate * Use Azure Pricing Calculator to predict the estimated monthly Azure bill for any Azure workload * Use Azure Cost Management to monitor cloud spending and increase organizational Accountability | 2 |  | New | SQL_CAF SQL Migration
Task | Initial Organization Alignment | * Assign a team for cloud adoption and cloud governance | 2 |  | New | SQL_CAF SQL Migration
Task | Skills Readiness Plan | * Identify the key cloud readiness courses required to be taken by IT and non-IT people in the organization | 2 |  | New | SQL_CAF SQL Migration
Task | Develop Cloud Adoption plan | * Convert the aspirational goals of the cloud adoption strategy into an actionable plan * Leverage the cloud adoption plan to guide technical efforts, in alignment with the business outcomes | 2 |  | New | SQL_CAF SQL Migration
User Story | CAF SQL Migration Readiness | Prepare the cloud environment for the planned changes | 2 |  | New | SQL_CAF SQL Migration
Task | Azure Setup Guide | * Familiarize with the features of the components needed to build the Azure environment * Organize resources * Manage access * Azure tools and approach * Governance, security, and compliance * Monitoring and reporting | 2 |  | New | SQL_CAF SQL Migration
Task | Pros and Cons of Landing Zones and Migration Tools Decision Guide | * Identify pros and cons of landing zones and migration tools for SQL Databases * Identify pros and cons of landing zones and migration tools for SQL Managed Instance * Identify pros and cons of landing zones and migration tools for SQL Virtual Machines | 2 |  | New | SQL_CAF SQL Migration
Task | Decide and Create Landing Zone | * Decide on target landing zone based on source SQL Server system capabilities, features and code * Compile and analyze the data to achieve landing zone goals. * Create landing zone for SQL database * Identify pros and cons of landing zones and migration tools for SQL Databases * Create landing zone for SQL Managed Instance * Create landing zone for SQL Virtual Machines | 2 |  | New | SQL_CAF SQL Migration
Task | Migrate SSIS, SSAS and SSRS to Azure | * Assess Fully managed service offering for migrating SSIS, SSAS and SSRS to Azure * Assess Infrastructure as a service for migrating SSIS, SSAS and SSRS to Azure | 2 |  | New | SQL_CAF SQL Migration
Task | Examples of Selecting Landing Zone | * Study examples of customer workloads and requirements and decide on an appropriate landing zone as well as the method of migration | 2 |  | New | SQL_CAF SQL Migration
Feature | CAF SQL Migration | Study available methods for SQL migration using Cloud Adoption Framework | 2 |  | New | SQL_CAF SQL Migration
User Story | Migration of On-Prem to Azure VM | Detailed assessment for migrating a work load from on-premises SQL to Azure Virtual Machine | 2 |  | New | SQL_CAF SQL Migration
Task | OnPrem to Azure Virtual Machine Overview | Familiarize with phases necessary to maximize performance while migrating a work load from on-premises SQL to Azure Virtual Machine | 2 |  | New | SQL_CAF SQL Migration
Task | Assessment | Use tools to assess migrating a work load from on-premises SQL to Azure Virtual Machine | 2 |  | New | SQL_CAF SQL Migration
Task | Deployment and Migration Testing | * Assess and choose deployment methods for migrating on-premises SQL to Azure Virtual Machine * Assess and choose testing methods for migrating on-premises SQL to Azure Virtual Machine | 2 |  | New | SQL_CAF SQL Migration
Task | Release and Additional Resources | Familiarize and practice hands-on lab for migrating a work load from on-premises SQL to Azure Virtual Machine | 2 |  | New | SQL_CAF SQL Migration
User Story | Migration - On-Prem to Azure SQL Database | Detailed assessment for migrating a work load from on-premises SQL to Azure SQL Database | 1 |  | New | SQL_CAF SQL Migration
Task | OnPrem to Azure Virtual Machine Overview | Familiarize with phases necessary to maximize performance while migrating a work load from on-premises SQL to Azure SQL Database | 2 |  | New | SQL_CAF SQL Migration
Task | Assessment | Use tools to assess migrating a work load from on-premises SQL to Azure SQL Database | 2 |  | New | SQL_CAF SQL Migration
Task | Deployment and Migration Testing | * Assess and choose deployment methods for migrating on-premises SQL to Azure SQL Database * Assess and choose testing methods for migrating on-premises SQL to Azure SQL Database | 2 |  | New | SQL_CAF SQL Migration
Task | Release and Additional Resources | Familiarize and practice hands-on lab for migrating a work load from on-premises SQL to Azure SQL Database | 2 |  | New | SQL_CAF SQL Migration
User Story | Migration - On-Prem to Azure SQL Managed Instance | Detailed assessment for migrating a work load from on-premises SQL to Azure Managed Instance | 2 |  | New | SQL_CAF SQL Migration
Task | OnPrem to Azure Managed Instance Overview | Familiarize with phases necessary to maximize performance while migrating a work load from on-premises SQL to Azure Managed Instance | 2 |  | New | SQL_CAF SQL Migration
Task | Assessment | Use tools to assess migrating a work load from on-premises SQL to Azure Managed Instance | 2 |  | New | SQL_CAF SQL Migration
Task | Deployment and Migration Testing | * Assess and choose deployment methods for migrating on-premises SQL to Azure Managed Instance * Assess and choose testing methods for migrating on-premises SQL to Azure Managed Instance | 2 |  | New | SQL_CAF SQL Migration
Task | Release and Additional Resources | Familiarize and practice hands-on lab for migrating a work load from on-premises SQL to Azure Managed Instance | 2 |  | New | SQL_CAF SQL Migration
Feature | CAF SQL Migration - Governance and Manage | Establish Governance and Operations Management for SQL migration | 2 |  | New | SQL_CAF SQL Migration
User Story | SQL Migration - Governance | Buid governance foundation for SQL Migration | 2 |  | New | SQL_CAF SQL Migration
Task | Organize resources | * Define a management group hierarchy using management groups, subscriptions, resource groups, and resources. * Define naming standard for components considering business and operational details. * Apply tags to Azure resources. | 2 |  | New | SQL_CAF SQL Migration
Task | Manage Access | * Assign RBAC roles at management group, subscription, resource group and resource levels. | 2 |  | New | SQL_CAF SQL Migration
Task | Manage Costs | * Perform cost analysis using Azure cloud costs. * Analyse actual, budget and forecast cost views. * Create budget and then configure alerts to track its threshold. * Review Azure recommendations to identify idle and underused resources, then take action. | 2 |  | New | SQL_CAF SQL Migration
Task | Governance, Security and Compliance | * Set up policy initiative, initiative definition and assignments using Azure Policy. * Create Azure Blueprint to orchestrate role assignments, policy assignments, Azure Resource Manager templates and Resource groups. * Deploy Azure resources using defined blueprint. * Review security status using Azure Security Center and then take action on the findings and recommendations. | 2 |  | New | SQL_CAF SQL Migration
Task | Monitoring and Reporting | * Detect and diagnose issues across applications and dependencies with Application Insights. * Correlate infrastructure issues with Azure Monitor for VMs and Azure Monitor for Containers. * Troubleshoot and diagnoise monitoring data using Log Analytics. * Create visualizations with Azure dashboards and workbooks. * Set up Service Health alerts in Azure Service Health to get notified about service issues, planned maintenance, or other changes that might affect Azure services. * Review and act on recommendations from Azure Advisor. | 2 |  | New | SQL_CAF SQL Migration
Task | Manage Governance (Inventory / Operational Compliance) | * Create an inventory of assets across multiple clouds * Establish controls and processes to ensure each state is properly configured and running in a well-governed environment | 2 |  | New | SQL_CAF SQL Migration
Feature | STAKEHOLDER SIGN OFF AND CLOSURE | Sign-off and Closure | 2 |  | New | SQL_CAF SQL Migration
User Story | CAF SQL Migration Project Review and Closer | Review and closure of project | 2 |  | New | SQL_CAF SQL Migration
Task | SQL Data Migration Project review meeting | Review meeting with stakeholders for tracking progress of the project | 2 |  | New | SQL_CAF SQL Migration
Task | SQL Data Migration documents review | Review migration documents with stakeholders | 2 |  | New | SQL_CAF SQL Migration
Task | Sign off on Project delivery | Provide project sign off | 2 |  | New | SQL_CAF SQL Migration